## First Year Program Phases
The Zero Waste Schools Program
First Year Program Phases
| August | September | October | November | December | January | February | March | April | May | June
Phase 1: Initial Meeting with Stakeholders. Includes program overview, program staff meeting with custodians/administrators/lead teachers, identification of existing clubs or Green Team, and school site walk-through to assess current practices. | bar: August to September
Phase 2: Pre-Program Waste Audit. Discuss current systems with custodial staff and identify key audit areas. Conduct a landfill audit of areas such as lunch, classrooms, staff room, and playground. | bar: August to September
Phase 3: Results Presentation. Present the results of the waste audit during a staff meeting. At this time, review program roll-out, sorting rules, and address questions. | bar: September to October
Phase 4: Stakeholder Training. Hold teacher, custodial, parent/PTA (if applicable), and paraprofessional trainings. | bar: September to November
Phase 5: Classroom Eduation. Attend a school-wide assembly to give a high-level program announcement.Visits to each classroom for 15-20 minutes to review program, sorting rules, and introduce new bins. | bar: October to December
Phase 6: Infrastructure Roll-Out. Classrooms bins, bathroom slim jims, staff room slim jims, and waste stations will be delivered, as applicable. | bar: November to January
Phase 7: Ongoing Education. Green Teams help supervise lunchtime sorting, educate their fellow peers on waste issues, and take action on problems they identify with support from ZWM staff. | bar: October to May
Phase 8: Follow-Up and Waste Audit. Conduct a waste audit to compare data, recommend changes if needed, and complete the ZWM Certification of the school site. | bar: April to June

## Continuation Year(s) Phases
Zero Waste Schools Program
Continuation Year(s) Program Phases
*Note that the first year of the program is the most intensive year. ZWM program staff will continue to be available to provide support to help schools achieve their waste goals and implement systems for long-term program sustainability.
| August | September | October | November | December | January | February | March | April | May | June
Phase 1: Check-In Meeting with Stakeholders. Meeting with relevant stakeholders to review the school site report, identify successes and opportunities for improvement from last year, and develop a plan for the school site for continuation. | bar: August to September
Phase 2: Re-Launch Green Team. Green Team relaunches meetings and ZWM staff will provide updates on recycling & composting practices. | bar: August to September
Phase 3: Waste Audit and Training Updates. Conduct a waste audit (in partnership with Green Team, if applicable) and present the results of the waste audit during a staff meeting. At this time, review successes from last year, plans for the current year, and address questions. | bar: September to October
Phase 4: Stakeholder Training. Hold teacher, custodial, parent/PTA (if applicable), and paraprofessional trainings as needed. | bar: September to November
Phase 5: Systems Evaluation and Updates. ZWM program staff will be available to school sites to troubleshoot any issues with lunch program waste, waste systems, or to answer general questions. Staff will be available to facilitate system changes or updates, as necessary. | bar: September to May
Phase 6: Ongoing Education. Green Teams will help supervise lunchtime sorting, educate their fellow peers on waste issues, and take action on problems they identify with support from ZWM staff. ZWM staff can help Green Teams work on special projects or initiatives as needed. | bar: September to May
Phase 7: Follow-Up and Waste Audit. Conduct a waste audit to compare data, recommend changes if needed, and complete the ZWM Certification of the school site. | bar: April to June